## Slide 1: DMAIEC Project Review Template
Project Name: EVE Sample Door Front Defect Reduction
Green Belt: Eugene Murray
Project Sponsor: Jeff Briley
Champion: Jeff Briley
Date: June 19, 2011

## Slide 2: DMAIEC Project Flow & Reviews
- Reviews Arranged and Scheduled by Black Belt
Separate Reviews are not recommended
Completed Activity
X
Champion/ Sponsor
Finance
BB-GB
MBB
Team Charter (including Business Case)
Map Process
VOC Data Collection
Specify CTQs
Approve Initial Charter
Review and Approve Outputs of Define Step
Review and Approve Outputs of Define Step
CTQs Measured
Process Stability
Process Capability
Baseline Sigma Calc
Focused Problem Statement
Review and Approve Outputs of Measure Step
Review and Approve Outputs of Measure Step
Identify Root Causes
Quantify Root Causes
Verify Root Causes
Review and Approve Focused Problem Statement & Updated Business Case
Review and Approve Outputs of Analyze Step
Review and Approve Outputs of Analyze Step
Select Solution (Including Trade Studies, Cost/Benefit Analysis)
Design Solution
Pilot Solution
Implement Solution
Review & Approve Selected Solution(s)
Review Implementation Progress
Support Trade Study, Cost/Benefit Analysis
Review Recommended Solutions
Review Implementation Progress
Institutionalize Improvement
Ongoing Control
Quantify Financial Results
Present Final Project Results, Lessons Learned
Project Closure
Validate Financial Results
Review Financial Results
Review Final Project Results, Lessons Learned
Review Financial Results
Review Final Project Results, Lessons Learned
Define
Analyze
Measure
Identify & Execute
Control
Review and Approve Initial Business Case

## Slide 3: Team Charter
Project Description
Problem & Goal Statement
Business Case
Scope

## Slide 4: Team Organizational Chart
Eugene Murray
Project Sponsor
Jeff Briley
Black Belt
Tony Word
Finance
Derek Oliver
Assembly Supervisor
Sharon Whitfield
Quality Auditor
Norma Guzman
Door Cell
Henry Wilson
Door Cell
EVE Sample Door Front Project

## Slide 5: Project Plan/Schedule
Step | Status | Actions – Previous Reviews
Define | 4-4-2011 | Complete 4-15-2011
Measure | 4-22-2011 | Complete 5-1-2011
Analyze | 4-29-2011 | Complete 5-15-2011
Improve | 5-2-2011 | Complete 6-1-2011
Control | 5-9-2011 | Complete 6-17-2011

## Slide 6: Map Process
Suppliers
Inputs
Process
Outputs
Customers
Finished Door
Vendor Supplied
Vendor Supplied
Vendor Supplied
Door ID Label
Shipping Carton
Machine Dept
Assembled Door & Frame
Finish Department
Assembly, package and ship a quality door front to the customer
Door Cell
Door Cell
Door Cell
Pull Door to
Match Frame
Hinge Door
To the Frame
Wrap door
And place in
carton
Place carton
In cart to be
shipped
Process Steps
Back Panel for Frame
Apply correct
Label to the
Door
Hinges
Defect Free Back
Door Hinged to Frame
Correct Label on Door
Door Packaged for Shipment
Door Cell
Door Cell

## Slide 7: VOC Data Collection/Specify CTQs
Quality
Sample Door
Front
Finished Door delivered
To the Door Cell
No Defects in Door
Correct Color
Correct Species of Wood
Correct Door Attached
To the Correct Frame
Door Drilled Correctly For Hinge
Door Hinged on Correct Side
Correct Label Attached
To Door ready for Shipment
Correct Label for Door
Label Attached Correctly & Centered
On Door
Need
Drivers
CTQs
General
Specific
Hard to measure
Easy to measure

## Slide 8
Hinge Table
Build Table
Pack Table
Pack Table
Door Cart
Door Cart
Door Cart
Foil Wrap
Door Cart
Door Cart
EVE Sample Door Front Flow Chart

## Slide 9: EVE Sample Door Defects
Chart: Number of Defects
| Door is Damaged | Damaged Frame | Hinges Showing Through Door | Label is NOT Centered on Door | Door has back attached but NOT correctly | Finish Defects | Door Does NOT Match Finish Goods Label | Label Missing | Label is NOT Marked Correctly | Staple Shoot Through Panel | Door Not Flush to Face Frame | Door Assembled on Wrong Side of Frame | Door Does NOT have a back attached | Door is Built Wrong
#REF! | 65 | 41 | 19 | 17 | 14 | 12 | 6 | 4 | 4 | 4 | 5 | 7 | 1 | 1

## Slide 10: Run Chart of Defects Per Day Before Improvements
Chart: 
 | 12 | 25 | 9 | 17 | 14 | 22 | 22 | 31 | 27 | 13 | 8
 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18

## Slide 11: Process Capability & Baseline Sigma
Current Capability

## Slide 12: Identify Root Causes
Dragging Doors in lieu of lifting
No TPM on Hinger
High number of
“major defect s on EVE Selling Center Doors
Drill Bit Set for Proper Depth
Hinger has dull Blades
Placing Door/Frames Face to Back
Dragging Doors in lieu of lifting
Method
Employee
Handling Damage
Machine
Placing door/frame on table with chips
Operator Not Properly Trained
Material
Wrong Finish Applied
Wrong Species of Wood
Environment
Dust//Chips on work table
Wong Hinge for Door
Wrong Label Applied to Door
AC Not Working/Employees Hot
Hinge Wrong Side of Door

## Slide 13: Select Solutions
Problem Verified Root Cause(s) Candidate Solutions
Damage to Door
And Frame
Handling Damage
Damage in Carts
Damage on Build
Table
Train Employees on Properly Handling
Put Dishwasher Racks in Carts
Put Padding on Build Tables
Lift and not Drag Doors/Frames
Ensure Doors/Frames are Face to Face
And Back to Back

## Slide 14: Run Chart Defects Per Day After Improvements
Chart: 
 | 3 | 3 | 0 | 4 | 5 | 3 | 3 | 1 | 2 | 0
 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2

## Slide 15: Project Results - Capability
Previous
Capability
Improved
Capability

## Slide 16: Project Closure
Improvements Made:
1. We 5s the Work Area (Sort, Set, Shine tools and equipment in the work area and at each work table)
2. Established a TPM (Total Preventative Maintenance Program on Hingers) for Operator to follow both daily and weekly checks
3. Installed Dishwasher racks in Carts for separation of doors and frames.
4. Trained employees on Properly Handling of Doors and Frames (face to face and back to back to minimize scratches, dents, nicks, etc.)
5. Trained employees on Proper Hinging Procedures (with posted procedures for different types of doors).
6. Coordinate properly training of employees in Finish department to ensure proper finish is applied to proper species of wood
7. Built bin for proper storage of various labels to be applied
8. Updated all work instructions
9. Established a Weekly Audit Process for Quality/Supervisors
10. Conduct random inspections of packaged product ready for shipment for defects

## Slide 17: Lessons Learned
Summarize Learnings Continued:
5s (Sort, Set, Shine, Standardize and Sustain) are critical elements in the workplace. They not only keep the workplace organized but also allow for a more efficient and safer work environment. We eliminated safety hazards by having a place for everything and having everything in its place.
Work Instructions are vital to quality. This process ensures that each operator (new, old, or temporary employee) follows the same process/procedures for assembly of the sample door front. It also allowed for us to identify Critical to Quality issues that needed special attention by the employees.
Following the TPM process for the hingers minimized downtime due no program in place which allowed for the hinger to run until they broke then maintenance was call in to fix the machine. Having a TPM required the operator to look over the hinger at the beginning and end of the hinger each day/week for proper set up and operation.
  About the work process
  About the team’s process
  About project results

## Slide 18: Lessons Learned
Summarize learnings
4. Training is important. Employees did not realize that handling cabinet doors and drawer fronts are like handling fine furniture. Different species of wood are harder and softer than others and are subject to dents, nick, etc. Having employees understand the species of wood and the characteristics of each along with handling face to face and back to back significantly reduced handling damage.
5. Communication among the team is important. Providing feedback several times a day back to the Finish Department was vital to “containing” finish defects, of wrong color, sags, runs, etc in the finished product enabled them to make corrective actions quicker which in turn minimized the amount of finished defects from coming up stream.
Communication to the operators as to the number and type of defects being found during the audits that were put into place. Having each operator stamp each packaged sample door front with their unique stamp provided accountability for defects found during each audit. The mere fact that we began auditing the process reduced the defect rate.
This was a small project but by focusing on it the team felt that it showed the employees involved that no matter how small a project it is important to ship and deliver a quality product to your customer each and every day.

## Slide 19: Replication Opportunities
Identify & list opportunities to replicate this project
  We are currently in the process of getting more six sigma training for all supervisors so that we can then have each of them focus on individual projects within their own departments.
List the Process Owner (Core/Enabling) responsible for replication
  Jeff Briley our Black Belt has initiated the efforts to get the plant more training. He has the support of our General Manager and they both are coordinated with our corporate office for support, i.e. training/budget dollars if not for this year for 2012.