## Idleness Expense
Gantt Chart - Idleness Expense
Symbol | Department | Percent of Capacity Used on Day | [9 empty] | Total Expense of Idleness | Lack of Work | Lack of Help | Lack of & Poor Material | Poor Planning | Remarks
|  | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100
Total

## Progress & Order
Gantt Chart - Progress & Order
Articles |  | Total Amount Ordered | January | February | March | April | May | June | July | August | September | October | November | December
Chocolate bars |  | 20
Vendor | Order Number | Amount Ordered
At the left of the upper chart is a list of articles to be procured. The amounts for which orders have been placed are shown in the column headed "Amount ordered." The dates between which deliveries are to be made are shown by angles. The amount to be delivered each month is shown by a figure at the left side of the space assigned to that month. The figure at the right side of each space shows the total amount to be delivered up to that date. If the amount due in any month is all received, a light line is drawn clear across the space representing that month. If only half the amount due is received, this line goes only half way across. In general, the length of the light line or the number of lines indicates the amount delivered that month. The heavy line shows cumulatively the amount delivered up to the date of the last entry. If will be noted that, if this line is drawn to the scale of the periods through which it passes, the distance from the end of the line to the current date will represent the amount of time deliveries are behind or ahead of schedule. It is thus seen that the short cumulative lines are the ones which require attention as they represent items that are farthest behind schedule. Z represents no deliveries. The top line on the lower chart is a summary of the individual orders and is represented on the upper chart by line A.

## Man Record
Gantt Chart - Man Record
Month Ending:
Name (Supv./Worker) | No | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
The daily space represents the amount of work a person should have done in a day, and also the time taken to do the work.
Estimated time for work done
Time on job for which we have no estimates
Solid line - cumulative estimated time for work done. Broken line - total time on work not estimated
The portion of the daily space through which no line is drawn shows how much the person has fallen behind what he was expected to do. The reasons for falling behind are indicated by the following symbols:
A - Absent
D - Defective work
G - Green operator
I - Lack of Instruction
M - Lack of or defective material
T - Tool Troubles or lack of tools
V - Holiday
X - Reason not clear